## Slide 1
Transform AKC-
For the best patient experience
Pilot QI Project Pack
Pilot site unit name: Royal Free

## Slide 2: 10 steps in QI
IHI Model for Improvement
KQIP Methodology
Agree an area for improvement using data
Prepare to lead a QI team
Understand your system and problem
Define project aim and scope
Identify and engage stakeholders
Define drivers and develop change ideas
Agree measures including baseline data
Test change ideas using PDSA cycles
Display data over time to understand impact
Sustain and share improvements

## Slide 3: Step 1: Area for improvement (Jan 2025)
Area for improvement : Health Literacy How do we document and measure health literacy levels within AKC population with aim to adapting patient education?

## Slide 4: Step 2: Prepare to lead a QI team

## Slide 5: Step 3: Understanding the system and problem Process Map, Fishbone, Pareto

## Slide 6: Step 3: Understanding the system (11 Feb 2025) Royal Free Ideal Process Map
Staff education understand why etc
Check staff confidence
New AKC pt (100%)
Explain and ask the SILS question to pt
Document answer on Vital Data
Staff education & what to do with your answer
How people interpret the Question
AKC follow up
STEPS
PROBLEM
POTENTIAL CHANGE IDEA
NEED MORE INFO
Form for sharing case studies
Script/prompt as natural as possible
Be ready to respond-act on answer
Add in comments box into SILS
5 -Always
Difficult conversations booklet
Adapt make every contact count
Pre & post confidence level
survey
Easy read education
Adapting what matters to you
Notes: 6

## Slide 7: Step 3 Fishbone– understanding low attendance of the patient education sessions – staff perspective (Dec 2025)
PROBLEM
Low patient attendance at the patient education sessions
PROCESSES
PATIENT FACTORS
COMMUNICATIONS
ENVIRONMENT
STAFF
TECHNOLOGY
Don’t advertise dates with other staff
Limited preparation
Digital exclusion/ literacy
No interest in attending
Work/ carers commitments
Patient in denial about disease/ condition
Symptom burden
Not having the right staff attend
Limited reminders – PES are excluded from the trust text messaging service
No information on the purpose / importance of attending these sessions
Cognition issues
Timings
Language barriers
Attending other appointments at same time/ day
Transport/ car parking
Location

## Slide 8: Step 3: Pareto Chart Reasons for not attending PES at Royal Free, patient perspective (Dec 2025)
Chart: Why patients did not attend PES
| Not answering phone | Feeling unwell | Didn’t know | Forgot | Not aware of event | Another personal comm | Work | Attend another app | Hospital admission | Couldn’t connect/on zoom call already | Childcare | No relative available to help | son attended diff name | Too short notice same day | child not well to continue | received cancellation email | Late
 | 10 | 5 | 5 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
 | 0.2381 | 0.35714 | 0.47619 | 0.54762 | 0.59524 | 0.64286 | 0.69048 | 0.7381 | 0.78571 | 0.83333 | 0.85714 | 0.88095 | 0.90476 | 0.92857 | 0.95238 | 0.97619 | 1
 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8

## Slide 9: Step 3: Pareto Chart Reasons for not attending PES at Tottenham Hale, patient perspective (Dec 2025)
Chart: Reasons for not attending
| Feeling unwell | Transport - relative could not bring them | Not interested | Attend another appoint | Had another personal commitment | Hospital admission | Had an emergency to deal with | Was not aware of the event
 | 4 | 3 | 3 | 3 | 2 | 1 | 1 | 1
 | 0.22222 | 0.38889 | 0.55556 | 0.72222 | 0.83333 | 0.88889 | 0.94444 | 1
 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8

## Slide 10: Step 4: Define project aim and scope

## Slide 11: Step 4: Project Aim
Measure health literacy
Use validated tool (SILS)
Put tool on vitaldata first
Use health literacy to shape care and education
31/12/25
Aim statement (draft)
Year 1
60% of AKC patients to have health literacy documented on Vitaldata using “Single Item Literacy Screen” tool by 31/12/25
Year 2 – how to use to shape care?

## Slide 12: Step 4: Project scope
What is in the project
All of patients in AKC service
Patricia (patient) idea
? Factsheet on info about what to expect about PD / Home HD / hospital HD
What is not in the project (yet)
? Involve earlier CKD patients later

## Slide 13
Step 4: Project Aim for 2026 (Dec 2025)
To deliver person-centred kidney care which is tailored to Royal Free patients meeting their health literary needs ensuring right decision and kidney treatment is made in a timely manner by Nov 2026

## Slide 14: Step 5: Identify and engage stakeholders

## Slide 15: Step 5: Identify & Engage -Stakeholder Map (Feb 2025)
More power in the project | Satisfy Opinion formers. Keep them satisfied with what is happening and review your analysis of their position regularly | Manage (key stakeholders) Key stakeholders should be fully engaged through full communication and consultation
Less power in the project | Monitor This group may be ignored if time and resources are stretched | Inform Patients often fall into this category. It may be helpful to take steps to increase their influence by organising them into groups or taking active consultative work
 | Less impact | More impact
Triumvirate Renal management
Other pilot sites
Renal IT
North central London
AKC consultant
Macius
KPA
Frailty Team & OT/PT
Administrative staff
RFH comms team
Community MDT
Csilla/Jo
KQIP – Transform AKC team
RFH AKC staff/ nurses/AHPs
KCUK
AKC/LCC patients
Renal staff
Population health team
Phlebotomy
Patients
Local orgs working with patients
Renal IT
Patients' relatives/carers
Learning disability acute liaison nurses
Royal Free charity
NKF
Dementia specialists
LKN
Kidney Research
DALS – trust language service provider

## Slide 16: Step 5 – Understanding stakeholders (Feb 2025)
Stakeholder | Who are they? Specify their roles but also consider their status, connections, whether they are supporters, peers, influencers, saboteurs, funders, delivery partners… | What do they know? About you, the subject, the language, the history, the context, the people | What do they fear? Costs, time, boredom, requests they can't meet, missing something, letting people down, more work, bad publicity | What do they want? To make a difference, save money hit targets, promotion, fame, a cause, their lunch….
AKC consultants | Sarah Hildebrand, Aine Burns, Cate Goodlad, Sai Duraisingham, Dakshina Jayasena, Colley Crawford, David Wheeler, Dorothea Nitsch | Supporters, influencers | More work, unaware of tool, what we do with it, not being able to meet communication needs, | To make a difference and improve experience
KPAs |  |  |  | 
Csilla/Jo |  |  |  | 
Frailty team OT & PT |  |  |  | 
KCUK |  |  |  | 
IT |  |  |  | 

## Slide 17: Step 5 – Engaging with stakeholders (Feb 2025) Using this 30/60/90-day template to plan how you will engage and communicate with your key stakeholders
 | Action(s) | Who will ensure this is completed
30 days (13 Mar) | Present to AKC team meeting 12.02.25-rolling agenda Meet with KCUK Clair re patient information sheet Send photos of waiting areas Script for asking questions Develop training for staff Escalate VD build Hot topics Planning for Birmingham | Jan/Csilla Macius Macius, Jo, core team Sarah
60 days (12 Apr) | AKC summit – present project Deliver training staff KPA newsletter item- update KPA team SILS tool live on VD Service line meeting and divisional board update. | Jo Henry
90 days (12 May) | Start SILS screening for new patients to AKC clinic Top tips to guide post SILS where to get help/advice Monitor number of SILS completed | 

## Slide 18: Step 6: Define drivers & developing change ideas Driver diagrams, Priority matrix

## Slide 19: Step 6: Define Drivers & Developing change ideas 1 – (April 2025)
Aim
60% of AKC patients to have health literacy documented on Vitaldata using “Single Item Literacy Screen” tool by 31/12/25
Staff awareness
Measurement
Staff education
Tools on Vital Data
Staff survey results end of June (Janette)
Roll out education by end ofJuly (Jo)
Vital data changes (Dave) add a field to Pt vital data to reflect offered
Run reports monthly (Dave)
Missed appointments data (Sarah)
Have MDT fill in SILS question (Lisa)
Chunk and check, teach back (Jo)

## Slide 20: Prioritising change ideas-Year 1 (April 2025)
30 Days
60/90 Days
Missed appointments data (Sarah)
Staff survey results end of June (Janette)
Add in awareness of question into session Jo
Look at questions in session evaluation (Juan)
Vital data changes (Dave) add a field to Pt vital data to reflect offered
Run reports monthly (Dave)
Someone from team to attend KPA meeting
Jo/Jan & Patricia
Roll out education by end ofJuly (Jo)
X3 sessions yearly
Why do people not attend education session? Audit and call pts (Princess & Zara). Start with St Pancreas, Edgware, Tottenham and Royal Free
Have MDT fill in SILS question (Lisa)
Invite pts by nurses, requirements for reimbursing pts, accessing sessions, advertising sessions, incentivise pts to attend
(Juan, Princess, Lalini, Magda) by Sept

## Slide 21: Step 6: Define Drivers & Developing change ideas (April 2025) Developing change ideas 2
Aim
The impact of recording the SILS score
So what?
Communication
Digital Literacy
Record language
Assessing level of education
Create visual tools
Deprivations scores
Using education questions
Asking advice about how to ask questions
Add level of education to electronic system
Missed appointments
Patients know best
RCA into reasons why pts don’t attend
Text reminder for appointment
Platforms asking what you would like
Tailor sessions to findings
Letters to patients (appropriate language)
Personalise communication
Modality-
treatment options
Audit sample patients – is there a correlation between SILS score and treatment
Patient education
Patient information session
Delivery method of sessions
Why do people not attend education session? Audit and call pts (Princess & Zara). Start with St Pancreas, Edgware, Tottenham and Royal Free
Someone from team to attend KPA meeting
Jo/Jan & Patricia
Add in awareness of question into session Jo
Look at questions in session evaluation (Juan)
X3 sessions yearly
Invite pts by nurses, requirements for reimbursing pts, accessing sessions, advertising sessions, incentivise pts to attend
(Juan, Princess, Lalini, Magda) by Sept

## Slide 22: Step 6: Developing change ideas 2 Dec 2025 The impact of recording the SILS score….So what?
Aim
To deliver person-centred kidney care which is tailored to Royal Free patients meeting their health literary needs ensuring right decision and kidney treatment is made in a timely manner by Nov 2026
Communication
Record language
Staff education
How could Harsh encourage patients to engage?
PES sessions being streamed - Arrange a teaching session on how to live stream
Review staff survey.
With new TAKC patient information folder does SILS score influence information. eg easy read vs standard versions
How do we use our patient feedback better? Pareto? Fishbone?
Modality-
treatment options
Letter audit comparing language used in letters 12 months ago to now. Using Hemingway app. (have we eliminated acronyms in our letters.
Patient education
Patient information session
Delivery method of sessions
Look at 10 pts that scores 5 how has this changed our communication. Consider looking at range of scores from 1-5.
Shared Decision Making - ask Ranjit and how do we collate in a different system? In particular map question % of those that feel PES session has help them make a decision? From each session.
Refresher session on HL tool kit – with sharing tips session
How do we map who has attended PES, date stamp, PRE ESRF, Preferred dialysis, accessing Tx w/up, pre-emptively listed, SILS score, language, Interpreter.
Review stake holder list. Sustainability Model tool
How does our project line up with Trust strategy
Sustainability Model tool
Renal Dept Goals
Trust goals
Patient information
Shared Decision Making
Understanding Digital literacy barriers
Departmental improvement plan
Assessing level of education?
Contact point for comms with patient
Use of Accurx for invite and reminders – calendar/poster

## Slide 23
Priorities for the next 3 months (Dec 2025)
Easy to do/ High impact – DO IT NOW (end Jan)
Hard to do/ Low impact – DELEGATE
Hard to do/ High impact – PLAN IT (end Feb)
Hard to do/ Low impact – PARK IT
How does this project fit into trust goals – complete the sustainability tool - Jo
Review patient education session posters/ flyers/ invite - Janette
Recirculate staff survey and compare to pre-education results - Janette
Arrange a teaching session on how to live stream - Juan
How can Harsh encourage other patients to attend patient education sessions
Stakeholder review - Jo
Review 10 patients who have a SILS=5 – how do we communicate with them – No name
Use of Accurx for invite and reminders – calendar/poster

## Slide 24
Driver diagram – Patient education session Dec 2025
Measurement
Patients
Staff
Give patients the option of attending virtually, in person of at their local unit
Review invite and posters – Janette and Juan
Ensure calendar of the sessions in visible in the clinic rooms
Need a template on the system for group appointments
Group appointments
Same slide set is used for each session/ site
For 100% attendance of patients at the Royal Free patient education session by Nov 2026
Send reminders
Tracking patient attendance

## Slide 25: Step 7: Agree measures including baseline data

## Slide 26: Step 7: National Measurement Strategy Renal Registry Dataset v5 – Care planning
Don’t worry about “preferred place of death” data unless you are focusing on conservative management
For data experts!
Transplant suitability & workup
Shared decision making
(transplant / dialysis / MCM)

## Slide 27: Step 7: National Measurement Strategy How will pilot sites measure project impact?
Pilot sites – please try to pull off an initial “care planning” dataset for your AKC patients by 31/1/25:
Renal registry data (or similar)
  Identify AKC patients – are some missing?
  Patient demographics
  Date of entry into AKC clinic / service
  Care planning data fields
    Shared decision making for future treatment options
    Transplant workup
    Future dialysis treatment choice
  You may want to include more detail if it helps you

## Slide 28: Step 7: Royal Free AKC/Project dataset - Jun 25-Dec 25

## Slide 29: Step 7 – Local project measurement strategy Define measures – year 1 Aim
Measure | Number or % Define numerator and denominator | Electronic or paper | Who is best person to collect the data | Sample size | How often (weekly/ monthly/ quarterly
No of patients with a SILS score (outcome measure) | % 60% of 1400 Total AKC pop | Electronic Vital data | Dave |  | monthly
Staff experience Pre/post staff survey 3-4 questions (30 staff) (process measure) | number | Electronic via teams' form | Janette | 30 | July (pre)

## Slide 30: Step 7 – Local project measurement strategy Define measures – year 1
Measure | Number or % Define numerator and denominator | Electronic or paper | Who is best person to collect the data | Sample size | How often (weekly/ monthly/ quarterly
Been invited to patient education session | numbers | Electronic spreadsheet | AKC team |  | 3x year
Attended a patient education session | numbers | Electronic Vital data | Dave |  | 3x year
Understanding why patients do not attend the education session |  |  | AKC team |  | 

## Slide 31: Step 7 – Local project measurement strategy Define measures – year 1
Measure | Number or % Define numerator and denominator | Electronic or paper | Who is best person to collect the data | Sample size | How often (weekly/ monthly/ quarterly
Attendance to clinic appointments (DNAs) 2 reporting methods |  |  |  |  | 
Treatment options |  |  |  |  | 
Language Level of education Interpreter | Numbers language field completed | Electronic Vital data | Dave |  | monthly

## Slide 32: Step 8: Test change ideas using PDSA cycles

## Slide 33: Step 8: Test change ideas using PDSA cycles To review and update the feedback questionnaire for PES

## Slide 34: Step 8: Test change ideas using PDSA cycles – staff survey

## Slide 35: Step 8: Test change ideas using PDSA cycles – add SILS to Vital Data

## Slide 36: Step 8: Test change ideas using PDSA cycles Understand why people did not attend PES at TH

## Slide 37: Step 8: Test change ideas using PDSA cycles why not attend PES at RF

## Slide 38: Step 8: Test change ideas using PDSA cycles Review evaluations at TH

## Slide 39: Step 8: Test change ideas using PDSA cycles Offering live streaming of PES

## Slide 40: Step 8: Patient education session PDSA’s Dec 2025
PDSA title | Date | Discussion | Next steps | Comments
Sending patient reminders | Dec 2025 | Although it’s takes time, staff are using the phone and via email. Also sending text messages | Continue but need to understand if this is working to increasing attendance | On going
Giving patients options for attending in person, local units or virtually | Dec 2025 | Plan A is to have patients attend in person. Plan B is patients attend on -line | Add into the invite email ‘in case you are unable to attend in person, please attend virtually either at home of in your local unit – here is the link:’ | On going
Review invite email and posters | Dec 2025 | Janette and Juan agreed to lead this PDSA. | Once final content version has been agreed with the team, to send to comms team and a few patients for comments | On going

## Slide 41: Step 9: Display data over time to understand impact

## Slide 42: SILS July to September report on VD (Target 10% monthly)
Chart: SILS Score
| July -launched | August | September
SILS Score 1 | 85 | 60 | 115
SILS Score 2 | 0 | 0 | 0
SILS Score 3 | 7 | 4 | 19
SILS Score 4 | 0 | 2 | 9
SILS Score 5 | 16 | 11 | 54
No score | 1 | 1 | 2
Step 9: Display data over time to understand impact
Chart: SILS report 2025
| July -launched | August | September
EKCC | 42 | 25 | 33
THKDC | 66 | 51 | 84
RFH | 44 | 20 | 54
SPC | 52 | 24 | 28
Total | 204 | 120 | 199

## Slide 43
Data
PES Feedback All attendees were satisfied or very satisfied.
64.7% had high health literacy, while 17.6% had good, and 17.6% had poor skills.
Reason for non-attendance:
- Mainly attributed to “distance related issues” (52.9%).
- Followed by “feeling unwell” and “forgetfulness” (23.55% respectively).
Quality of Information:
- 80% felt they were spoken to in a way they could understand
- 100% found the information helpful, specially hearing from other patients, observing dialysis equipment, dietary advice, and learning about conservative management.
Need for Improvement
The least helpful were low sound volume and bright lighting affecting screen visibility.

## Slide 44: Step 9: Display date over time Jan 2026 presented at UKKW

## Slide 45: Step 10: Sustain and share improvements

## Slide 46: Step 10: Sustain and share improvements Sustainability Model March 2026

## Slide 47: Step 10: Sustain and share improvements

## Slide 48: Archive

## Slide 49: Measurement checklist
Measure name – e.g. Shared future RRT choice | 
Why is it important? Understand whether progressing along care plan– if not why not? Target patients for action to improve care. If blank, why no data – try to fill in gaps Compare chosen and actual dialysis modality – root cause analysis (provide justification and links to organisation strategy) national targets, trust initiatives on frailty | 
Who owns the measure? eGFR>20 – CKD cohort; eGFR <20 AKC team – nurses complete page on Vitaldata (person responsible for making it happen) | 
Measure definition | What is the definition? eGFR<20 + rapidly progressing (spell it very clearly in words)
 | What data items do you need? See registry list for care planning items Date of encounter – clinic / education session
 | What is the calculation? words
 | Which patient groups are to be covered? Do you need to stratify? (clinic location – all 4 AKC clinic locations)
Goal setting | What is the numeric goal you are trying to achieve? 90% of eGFR <15 to have commenced shared decision making
 | Who is responsible for setting the goal? AKC team – Joanne, Sarah etc.
 | When will it be achieved by?

## Slide 50: Measurement - Process
Measure name - e.g. Shared future RRT choice | 
Collect | Is the data available? yes
 | Who is responsible for the data collection? AKC nurses + doctors enter data
 | What is the process for collecting the data – monthly RAG report – may need separate report
Analyse calculate measure & present results | What is the process for presenting data? Jan creates charts and presents to team quarterly report + longer annual report (Run chart, excel bar chart)
 | Who is responsible for the analysis? AKC team
 | How often is the analysis completed? Monthly (some) – quarterly - annually
Review | Where will the decisions be made based on results?
 | Who is responsible for acting on results?

## Slide 51
Royal Free
Patient education
& health literacy
Action plan should be agreed with your improvement team
List achievable actions and set dates for completion.
Once 90 days over – restart with 30/60/90 planning.
Use at every improvement team meeting asking are we on track? Anything else we need to do? Are the dates still achievable?
Within | We want to achieve … (actions) | We want to complete this by … (insert date)
30 days | Meet Kerry Lee (PhD student) about health literacy project Find out where we document language – what is it Who interprets for the patients – how do we identify whether they need it NHS tracker – will tell you the reading age (NHS readability checker) Confirm SILS as health literacy screening tool with AKC staff Work with David (data manager) to get SILS onto Vitaldata | 15/2/25
60 days | Test use of SILS tool in AKC (PDSA cycle – review what worked well and limitations – ? adjust / different tool) Team training around use of tool Raise awareness more widely in renal team / NHS trust Look at pre clinic leaflet – is it being sent out? Did they get it? Very dense/lots to do/ format to make action clearer/2nd part of letter Did they read it? You are welcome to bring someone with you Ask patients for feedback on preclinic letter | 15/3/25
90 days | Get SILS onto vitaldata ? Redesign preclinic leaflet | 15/3/25